## Sheet1
Tasks | Start Date | Duration | End Date
SRS Document | 2014-01-15 | 21 | 2014-02-05
Coding Standard | 2014-01-29 | 6 | 2014-02-04
Bug Tracking Policy | 2014-02-03 | 4 | 2014-02-07
Design User Interfaces | 2014-02-07 | 4 | 2014-02-11
Develop User Manual | 2014-02-11 | 2 | 2014-02-13
Risk Assessment | 2014-02-14 | 2 | 2014-02-16
Architectural Design for CTC Office and Signaling | 2014-02-17 | 3 | 2014-02-20
Design each major Architectural Component, and Interfaces | 2014-02-17 | 5 | 2014-02-22
Quality Assurance Plan, Specific Test Plan, and Setup Build Environ. | 2014-02-22 | 3 | 2014-02-25
Develop UML Designs for each Component | 2014-02-25 | 5 | 2014-03-02
Coordinate on Design Review Presentations | 2014-03-04 | 3 | 2014-03-07
Create Test Cases | 2014-03-09 | 3 | 2014-03-12
System Implementation (Classes) | 2014-03-13 | 19 | 2014-04-01
Sub-System Integration | 2014-03-17 | 21 | 2014-04-07
Test the System | 2014-04-08 | 5 | 2014-04-13
Create and Installation Package for System Deployment | 2014-04-13 | 3 | 2014-04-16
Buffer Week | 2014-04-16 | 7 | 2014-04-23
Due Dates:
Work Package 1: 02/14/14
Work Package 2: 03/27/14
Work Package 3: 04/24/2014