## Sheet1
Tasks | Start Date | Duration | End Date
SRS Document | 2014-01-15 | 21 | 2014-02-05
Coding Standard | 2014-01-29 | 6 | 2014-02-04
Bug Tracking Policy | 2014-02-03 | 4 | 2014-02-07
Design User Interfaces | 2014-02-07 | 4 | 2014-02-11
Develop User Manual | 2014-02-11 | 2 | 2014-02-13
Risk Assessment | 2014-02-14 | 2 | 2014-02-16
Architectural Design for CTC Office and Signaling | 2014-02-17 | 3 | 2014-02-20
Design each major Architectural Component, and Interfaces | 2014-02-17 | 5 | 2014-02-22
Quality Assurance Plan, Specific Test Plan, and Setup Build Environ. | 2014-02-22 | 3 | 2014-02-25
Develop UML Designs for each Component | 2014-03-01 | 2 | 2014-03-03
Coordinate on Design Review Presentations | 2014-03-04 | 2 | 2014-03-06
Create Test Cases | 2014-03-09 | 3 | 2014-03-12
Track Model - Create Test Plan | 2014-03-18 | 9 | 2014-03-27
Track Model - Create Architectual Design | 2014-03-18 | 9 | 2014-03-27
Track Model - Complete LoadTrackMap Class | 2014-03-18 | 9 | 2014-03-27
Track Model - Complete Block Class | 2014-03-18 | 9 | 2014-03-27
Track Model - Complete PowerGenerator Class | 2014-03-18 | 9 | 2014-03-27
Track Model - Complete Track Model Class | 2014-03-18 | 9 | 2014-03-27
Track Model - Complete TrackSwitch Class | 2014-03-18 | 9 | 2014-03-27
Track Controller - Design executable component | 2014-03-18 | 9 | 2014-03-27
Track Controller - Create Test Plan | 2014-03-18 | 9 | 2014-03-27
Track Controller - Create Architectual Design | 2014-03-18 | 9 | 2014-03-27
Track Controller - Complete SafetyTrackSpeed Class | 2014-03-18 | 9 | 2014-03-27
Track Controller - Complete RailwayCrossing Class | 2014-03-18 | 9 | 2014-03-27
Track Controller - Complete TrackStatus Class | 2014-03-18 | 9 | 2014-03-27
Track Controller - Complete ValidateBooleanLogic Class | 2014-03-18 | 9 | 2014-03-27
Track Controller - Complete TrackController Class | 2014-03-18 | 9 | 2014-03-27
Train Controller - Design executable component | 2014-03-18 | 9 | 2014-03-27
Train Controller - Create Test Plan | 2014-03-18 | 9 | 2014-03-27
Train Controller - Create Architectual Design | 2014-03-18 | 9 | 2014-03-27
Train Controller - Complete TrainControl Class | 2014-03-18 | 9 | 2014-03-27
Train Controller - Complete SafControl Class | 2014-03-18 | 9 | 2014-03-27
Train Controller - Complete GetTrainInfo Class | 2014-03-18 | 9 | 2014-03-27
Train Controller - Complete TrainControllerGUI Class | 2014-03-18 | 9 | 2014-03-27
CTC Office - Design executable component | 2014-03-18 | 9 | 2014-03-27
CTC Office - Create Test Plan | 2014-03-18 | 9 | 2014-03-27
CTC Office - Create Architectual Design | 2014-03-18 | 9 | 2014-03-27
CTC Office - Complete Train Class | 2014-03-18 | 9 | 2014-03-27
CTC Office - Complete Switch Class | 2014-03-18 | 9 | 2014-03-27
CTC Office - Complete CTC GUI Class | 2014-03-18 | 9 | 2014-03-27
CTC Office - Complete Stops Class | 2014-03-18 | 9 | 2014-03-27
CTC Office - Complete TrackBlock Class | 2014-03-18 | 9 | 2014-03-27
Track Model - Design executable component | 2014-03-18 | 9 | 2014-03-27
Track Model - Create Test Plan | 2014-03-18 | 9 | 2014-03-27
Track Model - Create Architectual Design | 2014-03-18 | 9 | 2014-03-27
Track Model - Complete Train Class | 2014-03-18 | 9 | 2014-03-27
Track Model - Complete Switch Class | 2014-03-18 | 9 | 2014-03-27
Track Model - Complete CTC GUI Class | 2014-03-18 | 9 | 2014-03-27
Track Model - Complete Stops Class | 2014-03-18 | 9 | 2014-03-27
Track Model - Complete TrackBlock Class | 2014-03-18 | 9 | 2014-03-27
Test System Sub-Components | 2014-03-25 | 2 | 2014-03-27
Test Complete System | 2014-04-08 | 5 | 2014-04-13
Create an Installation Package for System Development | 2014-04-13 | 3 | 2014-04-16
Buffer Week | 2014-04-16 | 7 | 2014-04-23
Due Dates:
Work Package 1: 02/14/14
Work Package 2: 03/27/14
Work Package 3: 04/24/2014
MileStone 1:
Prelimary Planning
03/07/14
MileStone 2:
Sysem and Component Design
03/27/14
MileStone 3:
System and Component Implementation and Testing and Documentation
04/16/14